## Slide 1: Hydrology DWG workshop conclusions
Vote on Orléans Resolution
  The Hydrology Domain Working Group recommends establishment of a WHOS portal to provide access to OGC standard-conformant water data services provided by National Hydrological Services.
Future/continuing work
  Groundwater
  Hydrologic Features (Lite in support of GFIE?)
  Sydney Adhoc meeting
  Timeseries+WaterML2:Part1+JSON encodings?
  Adoption/outreach/training?
    Relationship between OGC and RDA
Next workshop
  San Diego, July or September 2016?
6th, Workshop of OGC Hydro DWG, Orleans, BRGM, 21-23 Sep 2015

## Slide 2: Draft Groundwater workplan to an adopted OGC Standard
SWG Charter in development
  Complete by end September
  eVote by HDWG and OGC
Re-work draft standard document
  RFC etc
Aim for a vote on the standard in June 2016
6th, Workshop of OGC Hydro DWG, Orleans, BRGM, 21-23 Sep 2015

## Slide 3: Draft HY_Features workplan to an adopted OGC Standard
The following activities are planned with respect to “Hydrologic Features, Part 1: Conceptual model”:
  Prepare document incl. Annexes NOW
  SWG vote to release Hydrologic Features, Part 1: Conceptual model for public comment (HYF-P1). 2016 February (e-mail vote)
  Release HYF-P1 for public comment. 2016 March
  Consolidation of comments and edits to HYF-P1 document based on comments. 2016 June
  Recommendation of the candidate standard to the Membership.
  2016 June
  60 day IPR review period and associated TC e-vote to approve “Hydrologic Features, Part 1: Conceptual model” candidate standard as an adopted OGC Standard.
  Present to Chy-15 2016 December
6th, Workshop of OGC Hydro DWG, Orleans, BRGM, 21-23 Sep 2015

## Slide 4
And a very big thank you to Sylvain and Frédérique and staff of BRGM
6th, Workshop of OGC Hydro DWG, Orleans, BRGM, 21-23 Sep 2015